## Sheet1
SRS/Closure Scan - Rerunnable Solutions Delivery Plan
Solution | Run No. | PSA File Submission Deadline | HMRC Auto Response return deadline | HMRC Clerical Fall out response deadline
Multiple Periods | 1 | Mon, 26th Jun 17 | Wed, 16th Aug 17 | Thu, 16th Nov 17
Was In Scheme | 2 | Tue, 18th Jul 17 | Thu, 31st Aug 17 | Thu, 30th Nov 17
Scheme Financials | 3 | N/A | N/A | N/A
Employer Details | 4 | Tue, 25th Jul 17 | Tue, 29th Aug 17 | Wed, 29th Nov 17
Spouse Details | 5 | Tue, 1st Aug 17 | Tue, 5th Sept 17 | Tue, 5th Dec 17
Scheme Financials | 6 | N/A | N/A | N/A
Scheme Financials | 7 | N/A | N/A | N/A
Multiple Periods | 8 | Fri, 18th Aug 17 | Wed, 11th Oct 17 | Thu, 11th Jan 17
Employer Details | 9 | Tue, 5th Sep 17 | Tue, 10th Oct 17 | Wed, 10th Jan 17
Secondary Type 5 | 10 | Tue, 12th Sep 17 | Fri, 13th Oct 17 | Fri, 13th Jan 17
HMRC System Migration - Stabilization Period
Was In Scheme | 11 | Tue, 24th Oct 17 | Mon, 7th Dec 17 | Wed, 7th Mar 17
Spouse Details | 12 | Tue, 14th Nov 17 | Tue, 19th Dec 17 | Mon, 19th Mar 17
Multiple Periods | 13 | Tue, 14th Nov 17 | Wed, 10th Jan 18 | Tue, 10th Apr 18
Employer Details | 14 | Tue, 21st Nov 17 | Fri, 29th Dec 17 | Mon, 2nd Apr 18
Scheme Financials | 15 | N/A | N/A | N/A
Scheme Financials | 16 | N/A | N/A | N/A
Secondary Type 5 | 17 | Tue, 2nd Jan 18 | Fri, 1st Feb 18 | Tue, 1st May 18
Was In Scheme | 18 | Thu, 14th Dec 17 | Thu, 8th Feb 18 | Tue, 8th May 18
Spouse Details | 19 | Tue, 9th Jan 18 | Tue, 13th Feb 18 | Mon 14th May 18
Scheme Financials | 20 | N/A | N/A | N/A
Multiple Periods
Was In Scheme
Type 5
Scheme Financials
Scheme Financials
Scheme Finanacials
Employer Details
Spouse Details
Solutions
Start
Mon 03 Jul '17
Finish
Tue 30 Jan '18
Aug
Sep
Oct
Nov
Dec
Jan
Multiple Periods - July
Multiple Periods - September
Multiple Periods - December
WIS Phase 4 - August
HMRC System Migration
Mon 09 Oct '17 - Fri 27 Oct '17
Migration solution testing
Mon 23 Oct '17 - Fri 10 Nov '17
WIS Phase 4 - November
WIS Phase 4 - January